## Status of new roads
Date: | 2026-08-06
Highway Agreements, Transport Development Management (TDM)
Technical Approval (TA): | The drawings, designs and details are agreed.
Part 1: | Construction up to base course, kerbing, highway drainage complete, street lighting columns installed & connected (or 6 week lead in).
Part 2 : | Outstanding works from Part 1 completed, carriageway surface completed, Thames Water S104 Maintenance Certificate achieved, commencement of maintenance period.
Final Inspection leading to Adoption: | All outstanding works completed, Thames Water S104 Vesting Certificate achieved. Highway maintainable at public expense.
Note: To check if a road or street has been adopted as highway maintainable at public expense please refer to the List of adopted roads and streets.
List of adopted roads and streets: | https://www.swindon.gov.uk/downloads/download/878/list_of_adopted_roads_and_streets
Agreement No | Site Name | Ward | Parish | Road Names | Agreement | Development Company | TA Granted Y / N | Legal Agreement Signed Y / N | Part 1 Certificate Issued Y / N | Part 2 Certificate Issued Y / N
2825 | Ermin Street, Blunsdon | Blunsdon & Highworth | Blunsdon | Minerva Heights, Flora Close. | Section 38 | Newland Homes | Y | Y | Y | N
2834 | High Street, Blunsdon | Blunsdon & Highworth | Blunsdon | Fortuna Road. | Section 38 | Linden Homes | Y | Y | N | Y
2842 | South High Street Blunsdon, Newland Homes | Blunsdon & Highworth | Blunsdon | Skylark. | Section 38 | Newland Homes | Y | Y | Y | N
2846 | Holdcroft, Blunsdon | Blunsdon & Highworth | Blunsdon | Horseshoe Square, Forge Road, Anvil Street. | Section 38 | Hills Homes Developments Ltd | Y | Y | Y | N
2851 | Sams Lane, Blunsdon | Blunsdon & Highworth | Highworth | Ashanti Way; Jenkins Close; Flagstaff Avenue; Lang Mews; Blunts Rise; Aki Court. | Section 38 | Hayfield Homes | Y | N | N | N
2853 | Swindon Road, Highworth (Redlands) | Blunsdon & Highworth | Highworth | Utha Court, Juno gardens, Gold Close, Sword Avenue. | Section 38 | Backhouse Construction Ltd | Y | Y | Y | N
2854 | Blunsdon Hill, Blunsdon (Hill Cottage) | Blunsdon & Highworth | Blunsdon | Thames View, Ray Lane, Coln Close, Churn Close. | Section 38 | Backhouse Construction Ltd | Y | N | N | N
2855 | Via Alveus, Land off B4019, Broad Blunsdon | Blunsdon & Highworth | Blunsdon | Smithy Close, Farrier Street. | Section 38 | Greensquare Homes | Y | Y | N | N
2860 | Robins Gardens (Abbey Stadium) | Blunsdon & Highworth | Highworth | To be confirmed. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
2863 | Shrivenham Road, Highworth | Blunsdon & Highworth | Highworth | To be confirmed. | Section 38 | BDW South West | N | N | N | N
2864 | Land off Horseshoe Cresent, Blunsdon | Blunsdon & Highworth | Blunsdon | To be confirmed. | Section 38 | Hills Homes Developments Ltd | N | N | N | N
2832 | Land off Slipper Lane, Chiseldon | Chiseldon & Lawn | Chiseldon | Manor Rise. | Section 38 | Heratidge Building | Y | N | N | N
5002 | Commonhead - R1 + R4 | Chiseldon & Lawn | Central Swindon South | Knook Close, Ashcombe Close. | Section 38 | Redrow Homes | Y | Y | Y | N
5004 | Commonhead Boulevard & Avenue (P1a) | Chiseldon & Lawn | Central Swindon South | Landford Crescent, Polesdon Avenue, Wincombe Road, Sheldon Street. | Section 38 | Persimmon/Redrow | N | N | N | N
5005 | Commonhead | Chiseldon & Lawn | Central Swindon South | Corsley Close, Hartham Close, Biddestone Avenue. | section 38 | Redrow Homes | N | N | N | N
5007 | Commonhead - R2 + R3 | Chiseldon & Lawn | Central Swindon South | Iford Close, Hartham Close, Corsley Close & Chalcot Road (northern footpath). | Section 38 | Redrow Homes | Y | Y | Y | N
5008 | Commonhead - R5a | Chiseldon & Lawn | Central Swindon South | Lordswood, Ballyack Close, Pinkney Road. | Section 38 | Redrow Homes | Y | Y | Y | N
5009 | Commonhead - 1a Infrastructure | Chiseldon & Lawn | Central Swindon South | Homington Avenue. | Section 38 | Persimmon/Redrow | Y | Y | Y | N
5010 | Commonhead - R5b | Chiseldon & Lawn | Central Swindon South | Pythouse Close, Lordswood. | Section 38 | Redrow Homes | Y | Y | Y | N
5011 | Commonhead - 2nd Stage Infrastructure | Chiseldon & Lawn | Central Swindon South | Bushton Close, Axford Close, Homington Avenue, Berryfield, Coatley Close. | Section 38 | Persimmon/Redrow | Y | Y | N | N
5012 | Commonhead - P5 | Chiseldon & Lawn | Central Swindon South | Salthrop Rise, Rainscombe Road. | Section 38 | Persimmon Homes Ltd | Y | Y | Y | Y
5013 | Commonhead - R6 | Chiseldon & Lawn | Central Swindon South | Crofton Road, Chisbury Road, Rockley Close, Berryfield. | Section 38 | Redrow Homes | Y | Y | Y | N
5014 | Commonhead R7b JB50 | Chiseldon & Lawn | Central Swindon South | Clyffe Close. | Section 38 | Redrow Homes | Y | Y | N | N
5015 | Commonhead Road JB5 | Chiseldon & Lawn | Central Swindon South | To be confirmed. | Section 38 | Persimmon/Redrow | Y | N | N | N
5016 | Commonhead Phase 2A infrastructure | Chiseldon & Lawn | Central Swindon South | Homington Avenue. | Section 38 | Persimmon/Redrow | Y | N | N | N
5017 | Commonhead P9 | Chiseldon & Lawn | Central Swindon South | Lucknam Close, Homington Avenue. | Section 38 | Persimmon/Redrow | Y | N | N | N
5018 | Commonhead, Phase 10 (Badbury Park) | Chiseldon & Lawn | Central Swindon South | Cottles Close, Flintham, Oare Lane, Homington Avenue. | Section 38 | Persimmon Homes Ltd | Y | N | N | N
5019 | Commonhead Phase 3 infrastructure | Chiseldon & Lawn | Central Swindon South | Homington Avenue. | Section 38 | Redrow/Persimmon | Y | N | N | N
5020 | Commonhead P11 | Chiseldon & Lawn | Central Swindon South | Fosbury Crescent. | Section 38 | Persimmon Homes Ltd | Y | N | N | N
5021/A | Commonhead R8, 9, 10 & 11 (East) | Chiseldon & Lawn | Central Swindon South | Neston Close, Clouds Row, Baynton Street, Fosbury Crescent, Hurdcott Road. | Section 38 | Redrow Homes | Y | N | N | N
5021/B | Commonhead R8, 9, 10 & 11 (West) | Chiseldon & Lawn | Central Swindon South | Neston Close, Clouds Row, Baynton Street, Fosbury Crescent, Hurdcott Road. | Section 38 | Redrow Homes | Y | N | N | N
2824 | Headlands Grove | Gorse Hill & Pinehurst | Stratton St Margaret | Jutland Avenue, Argus Green, Calliope Crescent, Collingwood Crescent. | Section 38 | Bellway Homes Limited (South West) | Y | Y | Y | Y
2680 | Okus Trading Estate | Old Town | Central Swindon South | Okus Road; Celsus Grove; Chain Court; Yersin Court; Florey Court; Pennyroyal House; Germander House. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
2708 | Broome Manor / Marlborough Road Cycleways | Old Town | Central Swindon South | Marlborough Road. | Section 38 | Places for People Developments Ltd | Y | Y | N | N
2836 | Marlborough Park Phase 1A & B | Old Town | Central Swindon South | Pipers Way, Ayrton Road, Collins Road, Ginner Road, Nevinson Road, Pryde Close, Trevelyan Road. | Section 38 | Places for People Developments Ltd | Y | N | N | N
2839 | Land off Croft Road Residential | Old Town | Central Swindon South | Homeleaze. | Section 38 | Taylor Wimpey Ltd | Y | Y | N | N
2845 | Marlborough Park Design Your Home | Old Town | Central Swindon South | Jowett Close, Horsefield, Nevinson Road. | Section 38 | Places for People Developments Ltd | N | N | N | N
4002 | Wichelstowe STAr | Old Town | Central Swindon South | East Wichel Way; Staldon Road; Ravensdale; Brentfore Street; Langdean Road; Eyam Road; Offerton Road; Nunwick Way. | Section 38 | Taylor Wimpey Ltd | Y | Y | Y | Y
4101 | WV01 & WV05, East Wichel | Old Town | Central Swindon South | Dunsley Vale, Trecastle Road. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
4104 | Parcel WV04, east wichel | Old Town | Central Swindon South | Stonehenge Road; Staldon Road. | Section 38 | Taylor Wimpey Ltd | Y | Y | Y | N
4107 | Parcel WV07, east wichel | Old Town | Central Swindon South | Aivemore Road, Ravensdale, Offerton Road. | Section 38 | Taylor Wimpey Ltd | Y | Y | Y | N
4109 | Parcel WV09, East Wichel | Old Town | Central Swindon South | Stonehenge Road; Staldon Road; Trevello Road. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
4110 | Parcel WV10, east wichel | Old Town | Central Swindon South | Arnhill Road; East Wichel Way. | Section 38 | Taylor Wimpey Ltd | Y | Y | Y | N
4112 | Parcel WV12, East Wichel | Old Town | Central Swindon South | Trevello Road; East Wichel Way; Stonehenge Road. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
4113 | Parcel WV13, east wichel | Old Town | Central Swindon South | Barbrook Road; Cosdon Road; East Wichel Way. | Section 38 | Taylor Wimpey Ltd | Y | Y | NA | N
4117 | Parcel WV17 - East Wichel | Old Town | Central Swindon South | East Wichel Way; Eyam Road; Holne Road; Rylane. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
4118 | Parcel WV18 - East Wichel | Old Town | Central Swindon South | Scorhill Lane; Leaze Street. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4122 | Parcel WV22 - East Wichel | Old Town | Central Swindon South | Yelland Walk; Brentfore Street. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4123 | Parcel WV23 & WV26 - East Wichel | Old Town | Central Swindon South | Ewden Close. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4125 | Parcel WV25 - East Wichel | Old Town | Central Swindon South | Fernacre Road; Stannon Lane; Ewden Close; Culbone Road. | Section 38 | Taylor Wimpey Ltd | Y | Y | Y | N
4127 | Parcel WV27 - East Wichel | Old Town | Central Swindon South | Fernacre Road, Ewden Close. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4128 | Parcel WV28 - East Wichel | Old Town | Central Swindon South | Staldon Road; Boscawen Way; Fernacre Road. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4129 | Parcel WV29 - East Wichel | Old Town | Central Swindon South | Brentfore Street, Timoney Place, Langdean Road, East Wichel Way. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4130 | Parcel WV30, 31 - East Wichel | Old Town | Central Swindon South | Frogden Road; East Wichel Way; Langdean Road; Cornwood Road. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
4133 | Parcel WV33 & WV34 - East wichel | Old Town | Central Swindon South | Collard Close; East Wichel Way. | Section 38 | Taylor Wimpey Ltd | Y | Y | NA | N
4135 | Parcel WV 35 - East Wichel | Old Town | Central Swindon South | Frogden Road. | Section 38 | Marston Pubs | Y | Y | Y | Y
3006 | Area H6, Oakhurst, Swindon | Priory Vale | Haydon Wick | Callington Road; Southwold Close. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
3157 | Area H56(part), H57, H58 | Priory Vale | Haydon Wick | The Boulevard; Melstock Road; Fitzpiers Close; Edred Walk; Stinsford Crescent; Dydale Road; Lavinia Walk; Charborough House; Bockhampton House. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
3159 | Area H59, H60, H61 | Priory Vale | Haydon Wick | Queen Elizabeth Drive; Friday Street; Dydale Road; Melstock Road; Alicia Close. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
3176 | Area H76 & H77 (part) | Priory Vale | Haydon Wick | Grace Walk; Giles Road; White Eagle Road; Milbury Walk; Charmind Walk; Winterbourne Road. | Section 38 | Taylor Wimpey Ltd | Y | N | NA | N
3189 | Area H89, Haydon End | Priory Vale | Haydon Wick | Prospero Way. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
3190 | Area H90/91 - Phase 1 | Priory Vale | Haydon Wick | Havisham Drive; Prospero Way; Camberwell House; Bosworth House. | Section 38 | Taylor Wimpey Ltd | Y | Y | Y | N
3191 | Area H56b, Haydon End | Priory Vale | Haydon Wick | Dydale Road; Welland House; Florence House; Swancourt House; Damson Path; Damson Crescent; Greenwood Grove. | Section 38 | Bellway Homes Limited (South West) | Y | Y | Y | Y
3192/a | H92/H93, Haydon End | Priory Vale | Haydon Wick | Dydale Road; Markton Close. | Section 38 | Taylor Wimpey Ltd | Y | N | N | N
2862 | Land adjacent to Woodbine Terrace | Ridgeway | Liddington | Brook Road. | Section 38 | Lagan Homes | Y | N | N | N
7001/01 | Redlands Spine Road PH1 (Infrastructure) | Ridgeway | Wanborough | Redlands Way. | Section 38 | Vistry Homes / Bellway Homes (Bristol) | N | N | N | N
7001/1B | Redlands Phase 1 - Bellway | Ridgeway | Wanborough | To be confirmed. | Section 38 | Bellway Homes Limited (South West) | N | N | N | N
7001/1V | Redlands Phase 1 - Vistry | Ridgeway | Wanborough | Dairy Walk. Inmeads, Hangar fields, Clover Grove, Dockham. | Section 38 | Vistry Homes | N | N | N | N
7001/2 | Redlands Spine Road PH2 (Infrastructure) | Ridgeway | Wanborough | To be confirmed. | Section 38 | Vistry Homes / Bellway Homes (Bristol) | N | N | N | N
7001/2B | Redlands Phase 2 - Bellway | Ridgeway | Wanborough | To be confirmed. | Section 38 | Bellway Homes Limited (South West) | N | N | N | N
7001/2V | Redlands Phase 2 - Vistry | Ridgeway | Wanborough | To be confirmed. | Section 38 | Vistry Homes | N | N | N | N
7400/1 | Lotmead Phase 1 | Ridgeway | Wanborough | To be confirmed. | Section 38 | Countryside Partnerships | N | N | N | N
2805 | Tadpole Corner Priory Vale | St Andrews | St Andrews | Delius Close. | Section 38 | Crest Nicholson South West | Y | Y | Y | Y
2821 | Abbey Stadium - Primary Road | St Andrews | St Andrews | Richardson Road. | Section 38 | Landvest PCC Ltd | Y | N | N | N
2827 | Abbey Stadium - Zone A & B | St Andrews | St Andrews | Greycing Street, Millard Road, Batsford Crescent, The Arc, Richardson Road, Byers Close. | Section 38 | BDW South West | Y | N | N | N
2833 | Abbey Farm | St Andrews | St Andrews | Topaz Close, Amethyst Road, Coral Close, Onyx Close, Peridot Close, Diamond Crescent, Citrine Close, Jasper Close, Jade Close, Emerald Crescent, Sapphire Road, Garnet Crescent, Opal Road & Ruby Close. | Section 38 | Redrow Homes/Linden Homes | Y | Y | Y | N
2835 | The Triangle, Lady Lane, Swindon | St Andrews | St Andrews | Robinscroft (Blunsdon Meadow). | Section 38 | Greensquare Homes | Y | Y | Y | Y
3032 | H32 Estate Road | St Andrews | St Andrews | Wharncliffe Street. | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6001 | Tadpole Farm - Eastern Access (The Avenue) | St Andrews | St Andrews | William Morris Way. | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6002 | Tadpole Farm - Western Access Road | St Andrews | St Andrews | Greene Street. | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6003 | Tadpole Farm - Phase 1a | St Andrews | St Andrews | Webb Lane, John Ruskin Road, Rossetti Lane, Siddal Street, Beardsley Lane, De Morgan Crescent, Malory Close. | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6004 | Tadpole Farm - Phase 1b | St Andrews | St Andrews | Barber Place, Brantwood Close, Burne Jones Avenue, Eglantyne Avenue, The Rectangle, Toynbee Avenue, John Ruskin Road, Dawson Close, Ashbee Crescent, Jebb Close. | Section 38 | BDW South West | Y | Y | Y | Y
6005 | Tadpole Farm - Phase 2 | St Andrews | St Andrews | Millias Close, Woolner Road, Artisans Lane, John Ruskin Road, Rackham Close. | Section 38 | Crest Nicholson South West | Y | Y | N | N
6006 | Tadpole Farm - Phase 1c (Retail) | St Andrews | St Andrews | Burden Road. | Section 38 | Crest Nicholson South West | Y | N | N | N
6007 | Tadpole Farm - Phase 2.1 | St Andrews | St Andrews | Welby Close, Augustus Close, Pugin Close MacKay Crescent, Baillie Close, Blackwell Close, High Ground, Scott Close. | Section 38 | Bovis Homes (Western) | Y | N | N | N
6008 | Tadpole Farm - Phase 4.1 & 4.3 | St Andrews | St Andrews | Eastlake, Selwyn Road, Heygate Road, Pearson Road, Trellace Street, Shapland, Image Road. | Section 38 | Crest Nicholson South West | Y | Y | N | N
6009 | Tadpole Farm - Phase 2.2 | St Andrews | St Andrews | Gimson Crescent, Daneway, High Ground, Mackay Crescent, Stoneywell, The Leasowes. | Section 38 | BDW South West | Y | Y | Y | N
6010 | Tadpole Farm - Phase 4.8 (Phase 1) | St Andrews | St Andrews | Mackmurdo Avenue, Chatfield, Creswick, Maizey Road, Felstead, Horne Close. | Section 38 | Bellway Homes Limited (South West) | Y | Y | Y | N
6011 | Tadpole Farm - Phase 4.2 | St Andrews | St Andrews | Pearson Road. | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6012 | Tadpole Farm - Phase 4.9 | St Andrews | St Andrews | Mackmurdo Avenue, Mucha Close, Hanker Close, Lalique Close, Horta Close, Tiffany Close, Steinlen Close. | Section 38 | Bellway Homes Limited (South West) | Y | Y | N | N
6013 | Tadpole Farm - Phase 3.1 | St Andrews | St Andrews | Blanchard Road, Eastlake, Mathews Close, Jekyll Close. | Section 38 | Crest Nicholson South West | Y | N | N | N
6014 | Tadpole Farm - Phase 4.4 | St Andrews | St Andrews | Cherwell, Eastlake, Dearle Road, Eastlake, Pearson Road. | Section 38 | Crest Nicholson South West | Y | N | N | N
6015 | Tadpole Farm - Phase 2.3 | St Andrews | St Andrews | High Ground, Barnsley Close, Sexton Close, Rodmarton Close. | Section 38 | BDW South West | Y | Y | Y | N
6016 | Tadpole Farm - Phase 4.8 A | St Andrews | St Andrews | Maizey Road, Creswick, Jeffrey Close. | Section 38 | Crest Nicholson South West | Y | N | N | N
6017 | Tadpole Farm - Phase 4.5 & 4.6 (Phase 1) | St Andrews | St Andrews | Keohler Close, Image Road, Sherrer Lane, Dresser Close, Lumb Close, Eastlake, Kempe Lane, Newille Close, Irvine Close. | Section 38 | Crest Nicholson South West | Y | N | N | N
6018 | Tadpole Farm - Phase 3.3 & 3.4 | St Andrews | St Andrews | Blanchard Road, Cooper Close, Parsons Place, Whall Close, Van Erp Close. | Section 38 | Crest Nicholson South West | Y | N | N | N
6019 | Tadpole Farm - Phase 2.3A Custom Build | St Andrews | St Andrews | Ilett Crescent. | Section 38 | Crest Nicholson South West | Y | N | N | N
6020 | Tadpole Farm - Phase 3.2 | St Andrews | St Andrews | Kinsley Close, Gaskin Close, Southall Close, Eastlake, Armfield Road, Bayes Close, Faulkner Close, Mercer Close, Stickley Close, Blanchard Close. | Section 38 | Wain Homes | Y | Y | N | N
3031/02 | Area H31, H33, H34, H35 - Ph 2 | St Andrews | St Andrews | Dyson Road; Holst Road; Truscott Avenue; Arnell Crescent. | Section 38 | Matthew Homes | Y | Y | Y | Y
3031/04 | H31, H33, H34, H35 - Phase 4 | St Andrews | St Andrews | Easdale Street, Dyson Road, Truscott Avenue. | Section 38 | Matthew Homes | Y | Y | Y | Y
3031/05 | H31, H33, H34, H35 - Phase 5 | St Andrews | St Andrews | Vaughn Williams Way, Truscott Avenue, Easdale Street. | Section 38 | Matthew Homes | Y | Y | Y | Y
3035/01 | Land at Parcel H35a | St Andrews | St Andrews | Millgrove Street. | Section 38 | Crest Nicholson South West | Y | N | NA | N
3035/2 | Area H35B, Redhouse | St Andrews | St Andrews | Arnold Street; Dussek Place; Eastbury Way; Fitkin Court; Bainton House; Millgrove Street; Tippett Avenue; Truscott Avenue; Vaughan Williams Way; Frankel Avenue. | Section 38 | Bellway Homes Limited (South West) | Y | Y | NA | Y
3052/01 | H53 Access road | St Andrews | St Andrews | Hayburn Road. | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6006/A | Tadpole Farm - Phase 1c (Residential) | St Andrews | St Andrews | Burden Road. | Section 38 | Crest Nicholson South West | Y | Y | Y | Y
6017A | Tadpole Farm- Phase 4.5 & 4.6 (Phase 2) | St Andrews | St Andrews | Keohler Close, Image Road, Sherrer Lane, Dresser Close, Lumb Close, Eastlake, Kempe Lane, Newille Close, Irvine Close. | Section 38 | Crest Nicholson South West | Y | N | N | N
2843 | Former South Marston Hotel | St Margaret & South Marston | South Marston | Magdalene Close. | Section 38 | Bellway Homes Limited (South West) | Y | Y | Y | N
2849 | Greenbridge Road | St Margaret & South Marston | Stratton St Margaret | Smiths Lane, Crampton Square, Crampton Road (Extension), Greenbridge Road (Nos 1-5). | Section 38 | Keepmoat | Y | Y | N | N
2859 | Catsbrain Farm Onsite | St Margaret & South Marston | Stratton St Margaret | To be confirmed. | Section 38 | Persimmon Homes Ltd | Y | N | N | N
7000 | North and South Link Road (Symmetry Park) | St. Margaret and South Marston | South Marston | To be confirmed. | Section 38 | Triax Symmetry | N | N | N
7000/A | East and West Link Road (Symmetry Park) | St. Margaret and South Marston | South Marston | To be confirmed. | Section 38 | Triax Symmetry | N | N | N
7600/1 | South Marston Spine Road (Thornhill to Old Vic Lane) | St. Margaret and South Marston | South Marston | To be confirmed. | Section 38 | Taylor Wimpey Ltd / Vistry Ltd | N | N
2847 | Oakfield Campus | Walcot and Park North | Central Swindon South | Oakfield Avenue. | Section 38 | Nationwide Building Society | Y | Y | N | N
2838 | Berkeley Farm, Wroughton | Wroughton & Wichelstowe | Wroughton | Freeman Crescent, Bedford Street, Kings Road. | Section 38 | Linden Homes | Y | Y | Y | Y
2852 | Ridgeway Park, Wroughton | Wroughton & Wichelstowe | Wroughton | Old Bakery Road, Tall Conifers, Saxon Close, Preddy Close, Jutes Green, Pipistrelle Walk, Pottery Row, Hamm Lane, Watercress Way. | Section 38 | Bellway Homes Limited (South West) | Y | Y | N | N
2856 | Clevedon House, Woodland View, Wroughton | Wroughton & Wichelstowe | Wroughton | Clevedon Gardens. | Section 38 | Doric Developments (Bath) Ltd | Y | Y | Y | Y
2857 | Wroughton Closed Landfill | Wroughton & Wichelstowe | Wroughton | Arras Road, Brick Lane, Brown Jack Lane, Winchcombe Way, Gosling Grove. | Section 38 | Hills Homes Developments Ltd | Y | N | N | N
4201 | Middle Wichel Phase 0 Parcel 1 | Wroughton & Wichelstowe | Wroughton | Beckett Strand, Dalby Strand. | Section 38 | Wichelstowe LLP | Y | Y | Y | Y
4202 | Middle Wichel Phase 0 Parcel 2 & 3 | Wroughton & Wichelstowe | Wroughton | Semington Strand; Chaddington Strand. | Section 38 | Wichelstowe LLP | Y | Y | y | Y
4203 | Scott Way Extension | Wroughton & Wichelstowe | Wroughton | Scott Way. | Section 38 | Wichelstowe LLP | Y | N
4204 | Wichelstowe Parcel 4 | Wroughton & Wichelstowe | Wroughton | Pyrus Grove ( Blythe House), Wishford Row, Conference Road, Celt Close, Prunus Walk, Quince Avenue. | Section 38 | Wichelstowe LLP | Y | Y | N | N
4205 | Wichelstowe Parcel 5 | Wroughton & Wichelstowe | Wroughton | Marden Avenue, (Ferris House), Hodges Close, Letcombe Lane, Shippery Lane (Pates House / Mundays House / Stallard House). | Section 38 | Wichelstowe LLP | Y | Y | N | N
4206 | Wichelstowe Parcel 6 | Wroughton & Wichelstowe | Wroughton | Codford Lane, Golden Grive, Pippin Street, Russet Close. | Section 38 | Wichelstowe LLP | Y | Y | N | N
4207 | Wichelstowe Parcel 7 | Wroughton & Wichelstowe | Wroughton | To be confirmed. | Section 38 | Wichelstowe LLP | N | N | N | N
4208N | Wichelstowe Parcel 8 North | Wroughton & Wichelstowe | Wroughton | To be confirmed. | Section 38 | Wichelstowe LLP | N | N | N | N
4208S | Wichelstowe Parcel 8 South | Wroughton & Wichelstowe | Wroughton | To be confirmed. | Section 38 | Wichelstowe LLP | N | N | N | N
4209 | Wichelstowe Parcel 9 | Wroughton & Wichelstowe | Wroughton | To be confirmed. | Section 38 | Wichelstowe LLP | N | N | N | N
4210 | Wichelstowe Parcel 10 | Wroughton & Wichelstowe | Wroughton | To be confirmed. | Section 38 | Wichelstowe LLP | N | N | N | N
2838A | Berkeley Farm, Wroughton (Phase 2) | Wroughton & Wichelstowe | Wroughton | Kings Road, Waytes Close, Lower Close. | Section 38 | Linden Homes | Y | Y | Y | Y
4200/1 | Foxham Way to Mill Lane | Wroughton & Wichelstowe | Wroughton | Wichel Way. | Section 38 | Wichelstowe LLP | Y | Y | Y | N
4200/2 | Mill Lane to Scotts Way | Wroughton & Wichelstowe | Wroughton | Wichel Way. | Section 38 | Wichelstowe LLP | N | N | N | N
4200/3 | Scott Way Roundabout | Wroughton & Wichelstowe | Wroughton | Wichel Way. | Section 38 | Wichelstowe LLP | Y | N | N | N
4200/4 | Wichel Way CRHLL - Mill Lane to Peglars Way | Wroughton & Wichelstowe | Wroughton | Scott Way. | Section 38 | Wichelstowe LLP | N | N | N | N
2866 | Lowry Road, Marlborough Park Phase 2 | Old Town | Central Swindon South | To be confirmed. | Section 38 | Places for People Developments Ltd | N | N | N | N
7608 | Parcels R8 and R9, South Marston | St. Margaret and South Marston | South Marston | To be confirmed. | Section 38 | Taylor Wimpey Ltd | N | N | N | N

## Sheet1
Agreement No | Site Name | Ward | Parish | Road Names | Section 38/ 278/Minor Works | Dev - Company | TA Granted Y / N | Legal Agreement Signed Y / N | Part 1 Certificate Issued Y / N | Part 2 Certificate Issued Y / N
2825 | Ermin Street, Blunsdon | Blunsdon & Highworth | Blunsdon | Minerva Heights, Flora Close | Section 38 | Newland Homes | Y | Y | Y | N
2834 | High Street, Blunsdon | Blunsdon & Highworth | Blunsdon | Fortuna Road | Section 38 | Linden Homes | Y | Y | N | Y
2842 | South High Street Blunsdon, Newland Homes | Blunsdon & Highworth | Blunsdon | Skylark | Section 38 | Newland Homes | Y | Y | Y | N
2846 | Holdcroft, Blunsdon | Blunsdon & Highworth | Blunsdon | Horseshoe Square, Forge Road, Anvil Street | Section 38 | Hills Homes Developments Ltd | Y | Y | Y | N
2851 | Sams Lane, Blunsdon | Blunsdon & Highworth | Highworth | Ashanti Way; Jenkins Close; Flagstaff Avenue; Lang Mews; Blunts Rise; Aki Court | Section 38 | Hayfield Homes | Y | N | N | N
2853 | Swindon Road, Highworth (Redlands) | Blunsdon & Highworth | Highworth | Utha Court, Juno gardens, Gold Close, Sword Avenue | Section 38 | Backhouse Construction Ltd | Y | Y | Y | N
2854 | Blunsdon Hill, Blunsdon (Hill Cottage) | Blunsdon & Highworth | Blunsdon | Thames View, Ray Lane, Coln Close, Churn Close | Section 38 | Backhouse Construction Ltd | Y | N | N | N
2855 | Via Alveus, Land off B4019, Broad Blunsdon | Blunsdon & Highworth | Blunsdon | Smithy Close, Farrier Street | Section 38 | Greensquare Homes | Y | Y | N | N
2860 | Robins Gardens (Abbey Stadium) | Blunsdon & Highworth | Highworth | TBC (Liz to confirm) | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
2863 | Shrivenham Road, Highworth | Blunsdon & Highworth | Highworth |  | Section 38 | BDW South West | N | N
2864 | Land off Horseshoe Cresent, Blunsdon | Blunsdon & Highworth | Blunsdon | TBC (Liz to confirm) | Section 38 | Hills Homes Developments Ltd | N | N | N | N
2832 | Land off Slipper Lane, Chiseldon | Chiseldon & Lawn | Chiseldon | Manor Rise | Section 38 | Heratidge Building | Y | N | N | N
5002 | Commonhead - R1 + R4 | Chiseldon & Lawn | Central Swindon South | Knook Close, Ashcombe Close | Section 38 | Redrow Homes | Y | Y | Y | N
5004 | Commonhead Boulevard & Avenue (P1a) | Chiseldon & Lawn | Central Swindon South | Landford Crescent, Polesdon Avenue, Wincombe Road, Sheldon Street, | Section 38 | Persimmon/Redrow | N | N |  | N
5005 | Commonhead | Chiseldon & Lawn | Central Swindon South | Corsley Close, Hartham Close, Biddestone Avenue | section 38 | Redrow Homes | N | N |  | N
5007 | Commonhead - R2 + R3 | Chiseldon & Lawn | Central Swindon South | Iford Close, Hartham Close, Corsley Close & Chalcot Road (northern footpath) | Section 38 | Redrow Homes | Y | Y | Y | N
5008 | Commonhead - R5a | Chiseldon & Lawn | Central Swindon South | Lordswood, Ballyack Close, Pinkney Road | Section 38 | Redrow Homes | Y | Y | Y | N
5009 | Commonhead - 1a Infrastructure | Chiseldon & Lawn | Central Swindon South | Homington Avenue | Section 38 | Persimmon/Redrow | Y | Y | Y | N
5010 | Commonhead - R5b | Chiseldon & Lawn | Central Swindon South | Pythouse Close, Lordswood | Section 38 | Redrow Homes | Y | Y | Y | N
5011 | Commonhead - 2nd Stage Infrastructure | Chiseldon & Lawn | Central Swindon South | Bushton Close, Axford Close, Homington Avenue, Berryfield, Coatley Close | Section 38 | Persimmon/Redrow | Y | Y | N | N
5012 | Commonhead - P5 | Chiseldon & Lawn | Central Swindon South | Salthrop Rise, Rainscombe Road | Section 38 | Persimmon Homes Wessex | Y | Y | Y | Y
5013 | Commonhead - R6 | Chiseldon & Lawn | Central Swindon South | Crofton Road, Chisbury Road, Rockley Close, Berryfield | Section 38 | Redrow Homes | Y | Y | Y | N
5014 | Commonhead R7b JB50 | Chiseldon & Lawn | Central Swindon South | Clyffe Close | Section 38 | Redrow Homes | Y | Y | N | N
5015 | Commonhead Road JB5 | Chiseldon & Lawn | Central Swindon South | TBC (Liz to confirm) | Section 38 | Persimmon/Redrow | Y | N | N | N
5016 | Commonhead Phase 2A infrastructure | Chiseldon & Lawn | Central Swindon South | Homington Avenue | Section 38 | Persimmon/Redrow | Y | N | N | N
5017 | Commonhead P9 | Chiseldon & Lawn | Central Swindon South | Lucknam Close, Homington Avenue | Section 38 | Persimmon/Redrow | Y | N | N | N
5018 | Commonhead, Phase 10 (Badbury Park) | Chiseldon & Lawn | Central Swindon South | Cottles Close (JB18), Flintham (JB17), Oare Lane (JB19), Homington Avenue | Section 38 | Persimmon Homes Ltd | Y | N | N | N
5019 | Commonhead Phase 3 infrastructure | Chiseldon & Lawn | Central Swindon South | Homington Avenue | Section 38 | Redrow/Persimmon | Y | N | N | N
5020 | Commonhead P11 | Chiseldon & Lawn | Central Swindon South | Fosbury Crescent | Section 38 | Persimmon | Y | N | N | N
5021/A | Commonhead R8, 9, 10 & 11 (East) | Chiseldon & Lawn | Central Swindon South | Neston Close, Clouds Row, Baynton Street, Fosbury Crescent, Hurdcott Road | Section 38 | Redrow | Y | N | N | N
5021/B | Commonhead R8, 9, 10 & 11 (West) | Chiseldon & Lawn | Central Swindon South | Neston Close, Clouds Row, Baynton Street, Fosbury Crescent, Hurdcott Road | Section 38 | Redrow | Y | N | N | N
2824 | Headlands Grove | Gorse Hill & Pinehurst | Stratton St Margaret | Jutland Avenue, Argus Green, Calliope Crescent, Collingwood Crescent | Section 38 | Bellway Homes (Bristol) | Y | Y | Y | Y
2680 | Okus Trading Estate | Old Town | Central Swindon South | Okus Road; Celsus Grove; Chain Court; Yersin Court; Florey Court; Pennyroyal House; Germander House | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
2708 | Broome Manor / Marlborough Road Cycleways | Old Town | Central Swindon South | Marlborough Road | Section 38 | Places for People | Y | Y | N | N
2836 | Marlborough Park Phase 1A & B | Old Town | Central Swindon South | Pipers Way, Ayrton Road, Collins Road, Ginner Road, Nevinson Road, Pryde Close, Trevelyan Road | Section 38 | Places for People | Y | N | N | N
2839 | Land off Croft Road Residential | Old Town | Central Swindon South | Homeleaze | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | N | N
2845 | Marlborough Park Design Your Home | Old Town | Central Swindon South | Jowett Close, Horsefield (Nevinson Road??) | Section 38 | Places for People | N | N | N | N
4002 | Wichelstowe STAr | Old Town | Central Swindon South | East Wichel Way; Staldon Road; Ravensdale; Brentfore Street; Langdean Road; Eyam Road; Offerton Road; Nunwick Way | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | Y | Y
4101 | WV01 & WV05, East Wichel | Old Town | Central Swindon South | Dunsley Vale, Trecastle Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
4104 | Parcel WV04, east wichel | Old Town | Central Swindon South | Stonehenge Road; Staldon Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | Y | N
4107 | Parcel WV07, east wichel | Old Town | Central Swindon South | Aivemore Road, Ravensdale, Offerton Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | Y | N
4109 | Parcel WV09, East Wichel | Old Town | Central Swindon South | Stonehenge Road; Staldon Road; Trevello Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
4110 | Parcel WV10, east wichel | Old Town | Central Swindon South | Arnhill Road; East Wichel Way | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | Y | N
4112 | Parcel WV12, East Wichel | Old Town | Central Swindon South | Trevello Road; East Wichel Way; Stonehenge Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
4113 | Parcel WV13, east wichel | Old Town | Central Swindon South | Barbrook Road; Cosdon Road; East Wichel Way | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | NA | N
4117 | Parcel WV17 - East Wichel | Old Town | Central Swindon South | East Wichel Way; Eyam Road; Holne Road; Rylane | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
4118 | Parcel WV18 - East Wichel | Old Town | Central Swindon South | Scorhill Lane; Leaze Street | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4122 | Parcel WV22 - East Wichel | Old Town | Central Swindon South | Yelland Walk; Brentfore Street | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4123 | Parcel WV23 & WV26 - East Wichel | Old Town | Central Swindon South | Ewden Close | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4125 | Parcel WV25 - East Wichel | Old Town | Central Swindon South | Fernacre Road; Stannon Lane; Ewden Close; Culbone Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | Y | N
4127 | Parcel WV27 - East Wichel | Old Town | Central Swindon South | Fernacre Road, Ewden Close | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4128 | Parcel WV28 - East Wichel | Old Town | Central Swindon South | Staldon Road; Boscawen Way; Fernacre Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4129 | Parcel WV29 - East Wichel | Old Town | Central Swindon South | Brentfore Street, Timoney Place, Langdean Road, East Wichel Way | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4130 | Parcel WV30, 31 - East Wichel | Old Town | Central Swindon South | Frogden Road; East Wichel Way; Langdean Road; Cornwood Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
4133 | Parcel WV33 & WV34 - East wichel | Old Town | Central Swindon South | Collard Close; East Wichel Way | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | NA | N
4135 | Parcel WV 35 - East Wichel | Old Town | Central Swindon South | Frogden Road | Section 38 | Marston Pubs | Y | Y | Y | Y
3006 | Area H6, Oakhurst, Swindon | Priory Vale | Haydon Wick | Callington Road; Southwold Close | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
3157 | Area H56(part), H57, H58 | Priory Vale | Haydon Wick | The Boulevard; Melstock Road; Fitzpiers Close; Edred Walk; Stinsford Crescent; Dydale Road; Lavinia Walk; Charborough House; Bockhampton House; | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
3159 | Area H59, H60, H61 | Priory Vale | Haydon Wick | Queen Elizabeth Drive; Friday Street; Dydale Road; Melstock Road; Alicia Close | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
3176 | Area H76 & H77 (part) | Priory Vale | Haydon Wick | Grace Walk; Giles Road; White Eagle Road; Milbury Walk; Charmind Walk (Adopted); Winterbourne Road | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | NA | N
3189 | Area H89, Haydon End | Priory Vale | Haydon Wick | Prospero Way | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
3190 | Area H90/91 - Phase 1 | Priory Vale | Haydon Wick | Havisham Drive; Prospero Way; Camberwell House; Bosworth House | Section 38 | Taylor Wimpey - Oxfordshire | Y | Y | Y | N
3191 | Area H56b, Haydon End | Priory Vale | Haydon Wick | Dydale Road; Welland House; Florence House; Swancourt House; Damson Path; Damson Crescent; Greenwood Grove | Section 38 | Bellway Homes (Wessex) | Y | Y | Y | Y
3192/a | H92/H93, Haydon End | Priory Vale | Haydon Wick | Dydale Road; Markton Close | Section 38 | Taylor Wimpey - Oxfordshire | Y | N | N | N
2862 | Land adjacent to Woodbine Terrace | Ridgeway | Liddington | Brook Road | Section 38 | Lagan Homes | Y | N | N | N
7001/01 | Redlands Spine Road PH1 (Infrastructure) | Ridgeway | Wanborough | Redlands Way | Section 38 | Vistry Homes / Bellway Homes (Bristol) | N | N | N
7001/1B | Redlands Phase 1 - Bellway | Ridgeway | Wanborough | TBC (Liz to confirm) | Section 38 | Bellway Homes (Bristol) | N | N | N
7001/1V | Redlands Phase 1 - Vistry | Ridgeway | Wanborough | Dairy Walk. Inmeads, Hangar fields, Clover Grove, Dockham | Section 38 | Vistry Homes | N | N | N
7001/2 | Redlands Spine Road PH2 (Infrastructure) | Ridgeway | Wanborough | TBC (Liz to confirm) | Section 38 | Vistry Homes / Bellway Homes (Bristol) | N | N |  | N
7001/2B | Redlands Phase 2 - Bellway | Ridgeway | Wanborough | TBC (Liz to confirm) | Section 38 | Bellway Homes (Bristol) | N | N |  | N
7001/2V | Redlands Phase 2 - Vistry | Ridgeway | Wanborough | TBC (Liz to confirm) | Section 38 | Vistry Homes | N | N |  | N
7400/1 | Lotmead Phase 1 | Ridgeway | Wanborough | TBC (Liz to confirm) | Section 38 | Countryside Partnerships | N | N |  | N
2802 | Manor Road, Swindon | Rodbourne Cheney |  |  | Section 38 | Raglan HA | N | N | NA | NA
2844 | Pilgrim Close | Shaw | West Swindon | Pilgrim Close | Section 38/ Section 278 | Swindon Housing Development Company | Y | Y | N | Y
2805 | Tadpole Corner Priory Vale | St Andrews | St Andrews | Delius Close | Section 38 | Crest Nicholson South West | Y | Y | Y | Y
2821 | Abbey Stadium - Primary Road | St Andrews | St Andrews | Richardson Road | Section 38 | Landvest PCC Ltd | Y | N | N | N
2827 | Abbey Stadium - Zone A & B | St Andrews | St Andrews | Greycing Street, Millard Road, Batsford Crescent, The Arc, Richardson Road, Byers Close | Section 38 | Barratt Bristol | Y | N | N | N
2833 | Abbey Farm | St Andrews | St Andrews | Topaz Close ROAD 1 Amethyst Road ROAD 2, 2A AND 3 Coral Close ROAD 5 Onyx Close ROAD 2B Peridot Close ROAD 4 Diamond Crescent ROAD 7 AND 7C Citrine Close ROAD 6 Jasper Close ROAD 8 Jade Close ROAD 9 Emerald Crescent ROAD 10 & 12 Sapphire Road ROAD 11 Garnet Crescent ROAD 16 Opal Road ROAD 15 Ruby Close ROAD 13 | Section 38 | Redrow Homes/Linden Homes | Y | Y | Y | N
2835 | The Triangle, Lady Lane, Swindon | St Andrews | St Andrews | Robinscroft (Blunsdon Meadow) | Section 38 | Greensquare Homes | Y | Y | Y | Y
3032 | H32 Estate Road | St Andrews | St Andrews | Wharncliffe Street | Section 38 | Crest Nicholson South West | Y | Y | Y | DEED OF VARIATON REQ. BEFORE PART 2 CERT RELEASE
6001 | Tadpole Farm - Eastern Access (The Avenue) | St Andrews | St Andrews | William Morris Way | Section 38 | Crest Strategic Projects | Y | Y | Y | N
6002 | Tadpole Farm - Western Access Road | St Andrews | St Andrews | Greene Street | Section 38 | Crest Strategic Projects | Y | Y | Y | N
6003 | Tadpole Farm - Phase 1a | St Andrews | St Andrews | Webb Lane, John Ruskin Road, Rossetti Lane, Siddal Street, Beardsley Lane, De Morgan Crescent, Malory Close | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6004 | Tadpole Farm - Phase 1b | St Andrews | St Andrews | Barber Place, Brantwood Close, Burne Jones Avenue, Eglantyne Avenue, The Rectangle, Toynbee Avenue, John Ruskin Road, Dawson Close, Ashbee Crescent, Jebb Close | Section 38 | David Wilson Homes - Bristol | Y | Y | Y | Y
6005 | Tadpole Farm - Phase 2 | St Andrews | St Andrews | Millias Close, Woolner Road, Artisans Lane, John Ruskin Road, Rackham Close | Section 38 | Crest Nicholson South West | Y | Y | N | N
6006 | Tadpole Farm - Phase 1c (Retail) | St Andrews | St Andrews | Burden Road | Section 38 | Crest Nicholson South West | Y | N | N | N
6007 | Tadpole Farm - Phase 2.1 | St Andrews | St Andrews | Welby Close, Augustus Close, Pugin Close MacKay Crescent, Baillie Close, Blackwell Close, High Ground, Scott Close | Section 38 | Bovis Homes (Western) | Y | N | N | N
6008 | Tadpole Farm - Phase 4.1 & 4.3 | St Andrews | St Andrews | Eastlake, Selwyn Road, Heygate Road, Pearson Road, Trellace Street, Shapland, Image Road | Section 38 | Crest Nicholson South West | Y | Y | N | N
6009 | Tadpole Farm - Phase 2.2 | St Andrews | St Andrews | Gimson Crescent, Daneway, High Ground, Mackay Crescent, Stoneywell, The Leasowes | Section 38 | David Wilson Homes - Bristol | Y | Y | Y | N
6010 | Tadpole Farm - Phase 4.8 (Phase 1) | St Andrews | St Andrews | Mackmurdo Avenue, Chatfield, Creswick, Maizey Road, Felstead, Horne Close | Section 38 | Bellway Homes (Bristol) | Y | Y | Y | N
6011 | Tadpole Farm - Phase 4.2 | St Andrews | St Andrews | Pearson Road, | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6012 | Tadpole Farm - Phase 4.9 | St Andrews | St Andrews | Mackmurdo Avenue, Mucha Close, Hanker Close, Lalique Close, Horta Close, Tiffany Close, Steinlen Close | Section 38 | Bellway Homes (Bristol) | Y | Y | N | N
6013 | Tadpole Farm - Phase 3.1 | St Andrews | St Andrews | Blanchard Road, Eastlake, Mathews Close, Jekyll Close | Section 38 | Crest Nicholson South West | Y | N | N | N
6014 | Tadpole Farm - Phase 4.4 | St Andrews | St Andrews | Cherwell, Eastlake, Dearle Road, Eastlake, Pearson Road | Section 38 | Crest Nicholson South West | Y | N | N | N
6015 | Tadpole Farm - Phase 2.3 | St Andrews | St Andrews | High Ground, Barnsley Close, Sexton Close, Rodmarton Close | Section 38 | David Wilson Homes - Bristol | Y | Y | Y | N
6016 | Tadpole Farm - Phase 4.8 A | St Andrews | St Andrews | Maizey Road, Creswick, Jeffrey Close, | Section 38 | Crest Nicholson South West | Y | N | N | N
6017 | Tadpole Farm - Phase 4.5 & 4.6 (Phase 1) | St Andrews | St Andrews | Keohler Close, Image Road, Sherrer Lane, Dresser Close, Lumb Close, Eastlake, Kempe Lane, Newille Close, Irvine Close | Section 38 | Crest Nicholson South West | Y | N | N | N
6018 | Tadpole Farm - Phase 3.3 & 3.4 | St Andrews | St Andrews | Blanchard Road, Cooper Close, Parsons Place, Whall Close, Van Erp Close | Section 38 | Crest Nicholson South West | Y | N | N | N
6019 | Tadpole Farm - Phase 2.3A Custom Build | St Andrews | St Andrews | Ilett Crescent | Section 38 | Crest Nicholson South West | Y | N | N | N
6020 | Tadpole Farm - Phase 3.2 | St Andrews | St Andrews | Kinsley Close, Gaskin Close, Southall Close, Eastlake, Armfield Road, Bayes Close, Faulkner Close, Mercer Close, Stickley Close, Blanchard Close | Section 38 | Wain Homes | Y | Y |  | N
3031/02 | Area H31, H33, H34, H35 - Ph 2 | St Andrews | St Andrews | Dyson Road; Holst Road; Truscott Avenue; Arnell Crescent | Section 38 | Matthew Homes | Y | Y | Y | Y
3031/04 | H31, H33, H34, H35 - Phase 4 | St Andrews | St Andrews | Easdale Street, Dyson Road, Truscott Avenue | Section 38 | Matthew Homes | Y | Y | Y | Y
3031/05 | H31, H33, H34, H35 - Phase 5 | St Andrews | St Andrews | Vaughn Williams Way, Truscott Avenue, Easdale Street | Section 38 | Matthew Homes | Y | Y | Y | Y
3035/01 | Land at Parcel H35a | St Andrews | St Andrews | Millgrove Street | Section 38 | Crest Nicholson South West | Y | N | NA | N
3035/2 | Area H35B, Redhouse | St Andrews | St Andrews | Arnold Street; Dussek Place; Eastbury Way; Fitkin Court; Bainton House; Millgrove Street; Tippett Avenue; Truscott Avenue; Vaughan Williams Way; Frankel Avenue | Section 38 | Bellway Homes (Wessex) | Y | Y | NA | Y
3052/01 | H53 Access road | St Andrews | St Andrews | Hayburn Road | Section 38 | Crest Nicholson South West | Y | Y | Y | N
6006/A | Tadpole Farm - Phase 1c (Residential) | St Andrews | St Andrews | Burden Road | Section 38 | Crest Strategic Projects | Y | Y | Y | Y
6017A | Tadpole Farm- Phase 4.5 & 4.6 (Phase 2) | St Andrews | St Andrews | Keohler Close, Image Road, Sherrer Lane, Dresser Close, Lumb Close, Eastlake, Kempe Lane, Newille Close, Irvine Close | Section 38 | Crest Nicholson South West | Y | N | N | N
2843 | Former South Marston Hotel | St Margaret & South Marston | South Marston | Magdalene Close | Section 38 | Bellway Homes (Bristol) | Y | Y | Y | N
2849 | Greenbridge Road | St Margaret & South Marston | Stratton St Margaret | Smiths Lane, Crampton Square, Crampton Road (Extension), Greenbridge Road (Nos 1-5) | Section 38 | Keepmoat | Y | Y | N | N
2859 | Catsbrain Farm Onsite | St Margaret & South Marston | Stratton St Margaret | TBC (Liz to confirm) | Section 38 | Persimmon Homes Wessex | Y | N | N | N
7000 | North and South Link Road (Symmetry Park) | St. Margaret and South Marston | South Marston | TBC (Liz to confirm) | Section 38 | Triax Symmetry | N | N | N
7000/A | East and West Link Road (Symmetry Park) | St. Margaret and South Marston | South Marston | TBC (Liz to confirm) | Section 38 | Triax Symmetry | N | N | N
7600/1 | South Marston Spine Road (Thornhill to OVL) | St. Margaret and South Marston | South Marston | TBC (Liz to confirm) | Section 38 | Taylor Wimpey Ltd / Vistry Ltd | N | N
2847 | Oakfield Campus | Walcot and Park North | Central Swindon South | Oakfield Avenue | Section 38 | Nationwide Building Society | Y | Y | N | N
2838 | Berkeley Farm, Wroughton | Wroughton & Wichelstowe | Wroughton | Freeman Crescent, Bedford Street, Kings Road | Section 38 | Linden Homes | Y | Y | Y | Y
2852 | Ridgeway Park, Wroughton | Wroughton & Wichelstowe | Wroughton | Old Bakery Road, Tall Conifers, Saxon Close, Preddy Close, Jutes Green, Pipistrelle Walk, Pottery Row, Hamm Lane, Watercress Way | Section 38 | Bellway Homes Limited (South West) | Y | y | N | N
2856 | Clevedon House, Woodland View, Wroughton | Wroughton & Wichelstowe | Wroughton | Clevedon Gardens | Section 38 | Doric Developments (Bath) Ltd – (Parent Company) Ashford Homes Ltd | Y | Y | Y | Y
2857 | Wroughton Closed Landfill | Wroughton & Wichelstowe | Wroughton | Arras Road, Brick Lane, Brown Jack Lane, Winchcombe Way, Gosling Grove | Section 38 | Hills Homes Developments Ltd | Y | N | N | N
4008 | Canal, Middle Wichel | Wroughton & Wichelstowe | Wroughton |  | Section 38 | Swindon Borough Council | Y | NA | NA | NA
4201 | Middle Wichel Ph0 Parcel 1 | Wroughton & Wichelstowe | Wroughton | Beckett Strand, Dalby Strand | Section 38 | David Wilson Homes / JV | Y | Y | Y | Y
4202 | Middle Wichel Ph0 Parcel 2&3 | Wroughton & Wichelstowe | Wroughton | Semington Strand; Chaddington Strand | Section 38 | David Wilson Homes / JV | Y | Y | y | Y
4203 | Scott Way Extension | Wroughton & Wichelstowe | Wroughton | Scott Way | Section 38 | Wichelstowe LLP (SBC and DWH JV) | Y | N
4204 | Wichelstowe Parcel 4 | Wroughton & Wichelstowe | Wroughton | Pyrus Grove ( Blythe House), Wishford Row, Conference Road, Celt Close, Prunus Walk, Quince Avenue | Section 38 | Wichelstowe LLP (SBC and DWH JV) | Y | Y
4205 | PARCEL 5 | Wroughton & Wichelstowe | Wroughton | Marden Avenue, (Ferris House), Hodges Close, Letcombe Lane, Shippery Lane (Pates House / Mundays House / Stallard House) | Section 38 | Wichelstowe LLP (SBC and DWH JV) | Y | Y | N | N
4206 | PARCEL 6 | Wroughton & Wichelstowe | Wroughton | Codford Lane, Golden Grive, Pippin Street, Russet Close | Section 38 | Wichelstowe LLP (SBC and DWH JV) | Y | Y |  | N
4207 | PARCEL 7 | Wroughton & Wichelstowe | Wroughton | TBC (Liz to confirm) | Section 38 | Wichelstowe LLP (SBC and DWH JV) | N | N |  | N
4208N | PARCEL 8 North, Wichelstowe | Wroughton & Wichelstowe | Wroughton | TBC (Liz to confirm) | Section 38 | Wichelstowe LLP (SBC and DWH JV) | N | N |  | N
4208S | PARCEL 8 South, Wichelstowe | Wroughton & Wichelstowe | Wroughton | TBC (Liz to confirm) | Section 38 | Wichelstowe LLP (SBC and DWH JV) | N | N |  | N
4209 | PARCEL 9 | Wroughton & Wichelstowe | Wroughton | TBC (Liz to confirm) | Section 38 | Wichelstowe LLP (SBC and DWH JV) | N | N |  | N
4210 | PARCEL 10 | Wroughton & Wichelstowe | Wroughton | TBC (Liz to confirm) | Section 38 | Wichelstowe LLP (SBC and DWH JV) | N | N |  | N
2838A | Berkeley Farm, Wroughton (Phase 2) | Wroughton & Wichelstowe | Wroughton | Kings Road, Waytes Close, Lower Close | Section 38 | Linden Homes | Y | Y | Y | Y
4200/1 | FOXHAM WAY TO MILL LANE (SOUTH OF PARCEL 5) | Wroughton & Wichelstowe | Wroughton | Wichel Way | Section 38 | Wichelstowe LLP (SBC and DWH JV) | Y | Y | Y | N
4200/2 | MILL LANE TO SCOTT WAY | Wroughton & Wichelstowe | Wroughton | Wichel Way | Section 38 | Wichelstowe LLP (SBC and DWH JV) |  |  |  | N
4200/3 | Scott Way Roundabout | Wroughton & Wichelstowe | Wroughton | Wichel Way | Section 38 | Wichelstowe LLP (SBC and DWH JV) | Y | N
4200/4 | Wichel Way CRHLL Mill Lane to Peglars Way H7 | Wroughton & Wichelstowe | Wroughton | Scott Way | Section 38 | Wichelstowe LLP (SBC and DWH JV)
2866 | Lowry Road, Marlborough Park Phase 2 PfP | Old Town | Central Swindon South | TBC (Liz to confirm) | Section 38 | Places for People Developments Ltd
7608 | Parcels R8 and R9, South Marston | St. Margaret and South Marston | South Marston | TBC (Liz to confirm) | Section 38 | Taylor Wimpey Ltd | N | N
Note on E127: Steven Sanders: SNN1393
Note on J7: Mark Woolford: Issued with Caveat. Bond reduced to £800k
Note on K1: Menna Stapley: Part 2 Cert Issued Y/N